Work Breakdown Structure (WBS)

Local Sports Tournament & Bracket Manager: Problem Statement #54

Sushanth S Rao, PES1UG24CS485, BPS54

Effort figures are my own planning estimates in hours.

# 1. WBS Hierarchy

| WBS ID | Work package | Deliverable | Effort (h) | Target |
| --- | --- | --- | --- | --- |
| 1 | Project Management |  |  |  |
| 1.1 | Create GitHub repository and folder structure | Repository | 1 | Week 1 |
| 1.2 | Set up Jira (Kanban and Scrum boards, epics, backlog) | Jira board | 3 | Week 1 |
| 1.3 | Sprint planning and review (2 sprints) | Sprint reports | 3 | Weeks 2–3 |
| 2 | Requirements Engineering |  |  |  |
| 2.1 | Elicit FR and NFR (5 FR + 2 NFR) | Requirements table | 3 | Week 1 |
| 2.2 | Model use cases and write UC-04 flow specification | Use-case diagram, flow spec | 4 | Week 1 |
| 2.3 | Build Requirements Traceability Matrix | RTM | 2 | Week 2 |
| 2.4 | Write SRS (IEEE 830 format) | SRS document | 5 | Week 2 |
| 3 | Design |  |  |  |
| 3.1 | Choose architecture pattern (layered + MVC) | Design decision | 1 | Week 2 |
| 3.2 | Draw architecture diagram | Architecture diagram | 3 | Week 2 |
| 3.3 | Design data model (teams, players, matches, brackets, scores, standings) | Data model | 3 | Week 3 |
| 4 | Implementation |  |  |  |
| 4.1 | Registration Service (FR-002) | Module + unit tests | 6 | Week 3 |
| 4.2 | Bracket Engine: seeding, byes, advancement (FR-001, FR-004) | Module + unit tests | 10 | Weeks 3–4 |
| 4.3 | Score Service with validation (FR-003) | Module + unit tests | 5 | Week 4 |
| 4.4 | Standings Service with tiebreakers (FR-005, NFR-001) | Module + unit tests | 8 | Week 4 |
| 4.5 | Auth & Role Service and Notification Service | Modules | 5 | Week 4 |
| 4.6 | Web UI (registration, score entry, bracket, standings) | UI pages | 8 | Weeks 4–5 |
| 4.7 | Use GitHub Copilot for code generation; capture evidence | Copilot screenshots / repo link | 2 | Weeks 3–5 |
| 5 | Testing |  |  |  |
| 5.1 | Write and run test cases TC-001 to TC-010 | Test report | 5 | Week 5 |
| 5.2 | Record defects (5 bugs) in bug report | Bug report | 2 | Week 5 |
| 5.3 | Fix bugs with vibe coding and retest; testing practice exercise | Fixed repository link | 6 | Week 6 |
| 5.4 | Performance check of standings (≤ 200 ms) | Benchmark result | 3 | Week 6 |
| 6 | Deployment |  |  |  |
| 6.1 | Environment setup and hosting | Running environment | 3 | Week 6 |
| 6.2 | Uptime monitoring setup (NFR-002) | Monitoring config | 2 | Week 6 |
| 7 | Documentation and Submission |  |  |  |
| 7.1 | Write main README indexing all folders | README | 2 | Week 6 |
| 7.2 | Upload all deliverables to GitHub folders and verify links | Final repository | 2 | Week 6 |

Total estimated effort: 97 hours.

# 2. Work Packages by Phase

| Phase | Effort (h) | Share |
| --- | --- | --- |
| Project Management | 7 | 7% |
| Requirements Engineering | 14 | 14% |
| Design | 7 | 7% |
| Implementation | 44 | 45% |
| Testing | 16 | 16% |
| Deployment | 5 | 5% |
| Documentation and Submission | 4 | 4% |

# 3. Milestones

| Milestone | Criteria | Target |
| --- | --- | --- |
| M1 – Requirements baselined | Requirements table, use cases, RTM and SRS complete | End of Week 2 |
| M2 – Design complete | Architecture diagram and data model approved | End of Week 3 |
| M3 – Implementation complete | All five services and UI working | End of Week 5 |
| M4 – Tested and fixed | All test cases run, bugs fixed and retested | End of Week 6 |
| M5 – Submission | All six folders and README uploaded to GitHub | End of Week 6 |

# 4. Dependencies and Assumptions

Implementation depends on the SRS and architecture (phases 2 and 3).

The testing exercise (5.3) depends on receiving the instructor's game repository.

Estimates are for one person; actual effort should be compared with these figures in the sprint reflection.